## Sheet1
|  | Artefact | Format | PM | Electrical Team | Civl Structural Team | Classification | Est Labour Hours | Timeline | Notes
1 |  | Project Management | [6 empty] | Start date plus x days
| 1 | Project Management Plan (PMP) | Report | X |  |  | Mandatory | 10 | 5
| 2 | Project Organisation Chart | Chart | X |  |  | Optional | 5 | 5
| 3 | Project Communication and Interface Matrix | Excel File | X |  |  | Mandatory | 5 | 5
| 4 | Project Programme (Microsoft Project) | MS Project file | X |  |  | Mandatory | 5 | 5
| 5 | Quality Management Plan | Report | X |  |  | Mandatory | 10 | 5
| 6 | Project Master Document Register | Excel File | X |  |  | Mandatory | 5 | 5
| 7 | Project Risk Register | Excel File | X |  |  | Mandatory | 10 | 15
| 8 | HSE Register | Excel File | X |  |  | Mandatory | 10 | 15
| 9 | Monthly Progress Report | Report | X |  |  | Mandatory | 15 | N/A
| 10 | Weekly Action Tracker | Excel File | X |  |  | Mandatory | 12 | N/A
| 11 | Final Report / Close out Report (after each Stage) | Report | X |  |  | Mandatory | 20 | 60
2 |  | Electrical
| 1 | Electrical Design Basis Statement | Report |  | X |  | Mandatory | 80 | 20
| 2 | Grid Code Requirement Statement | Report |  | X |  | Mandatory | 20 | 20
| 3 | Basis HV Topology Report | Report |  | X |  | Mandatory | 60 | 20
| 4 | Power System Analysis Report | Report |  | X |  | Mandatory | 80 | 65
| 5 | Power System Model - Digsilent (Steady State) | Model |  | X |  | Mandatory | 80 | 60
| 6 | Power System Model - PSCAD (Switching) | Model |  | X |  | Mandatory | 80 | 60
| 7 | OVERALL NETWORK SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 20 | 20
| 8 | SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 20 | 20
| 9 | PROTECTION SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
| 10 | SCADA & CONTROL BLOCK DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
| 11 | COMMUNICATION BLOCK DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
| 12 | LVAC & LVDC SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 30 | 30
| 13 | CELLAR DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 14 | CABLE DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 15 | MAIN DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 16 | COOLER DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 17 | UTILITY DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 18 | MAIN DECK CABLE LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 19 | ROOF DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 20 | ELEVATION LOOKING NORTH LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 21 | ELEVATION LOOKING EAST LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
| 22 | Technical requriement specification for main components - EHV GIS | Specification |  | X |  | Mandatory | 20 | 35
| 23 | Technical requriement specification for main components - MV GIS | Specification |  | X |  | Mandatory | 20 | 35
| 24 | Technical requriement specification for main components - Power Transformers | Specification |  | X |  | Mandatory | 20 | 35
| 25 | Technical requriement specification for main components - Shunt Reactors | Specification |  | X |  | Mandatory | 20 | 35
| 26 | Technical requriement specification for main components - EHV/MV Cables (connections to TF and GIS) | Specification |  | X |  | Mandatory | 20 | 35
| 27 | Technical requriement specificaiton of earthing, lightning systems | Specification |  | X |  | Mandatory | 25 | 35
| 28 | Technical requriement specification of Protection, SCADA, Communication systems, Access Control Monitoring, etc. | Specification |  | X |  | Mandatory | 30 | 35
| 29 | HAZID Workshop (Overall OSS) | Report |  | X |  | Optional | 40 | 35
3 |  | Civil and Structural
| 1 | Comparison Studies and assessments - Comparison of anodes and ICCP | Report |  |  | X | Mandatory | 40 | 20
| 2 | Comparison Studies and assessments - Installation comparison | Report |  |  | X | Mandatory | 40 | 20
| 3 | Comparison Studies and assessments - High level comparison of topside braced design and stress skin design | Report |  |  | X | Mandatory | 40 | 20
| 4 | OSS Design Basis - Topside / Jacket | Report |  |  | X | Mandatory | 60 | 30
| 5 | OSS General Arrangement - Jacket | Report |  |  | X | Mandatory | 60 | 30
| 6 | OSS J-tube Appurtenance Arrangement | Drawing |  |  | X | Mandatory | 40 | 35
| 7 | OSS Topside 3-D Model | Model |  |  | X | Mandatory | 150 | 40
| 8 | OSS Substructure 3-D Model | Model |  |  | X | Mandatory | 150 | 40
| 9 | OSS Weight Report - Topside/Jacket | Report |  |  | X | Mandatory | 40 | 40
| 10 | Material Take-off (MTO) - Jacket (Primary steels focused) | List |  |  | X | Mandatory | 40 | 45
| 11 | Material Take-off (MTO) - Topside (Primary steels focused) | List |  |  | X | Mandatory | 40 | 45
| 12 | Design Report - Structural designs, Loadout and T&I concept - Jacket | Report |  |  | X | Mandatory | 60 | 45
| 13 | Design Report - Structural designs, Load out and T&I concept - Topside | Report |  |  | X | Mandatory | 60 | 45
| 14 | Cost Estimation Report - Topside / Substructure / T&I / Commissioning | Report |  |  | X | Optional | 40 | 50
| 15 | Preliminary EPCI Project Execution Plan | Report |  |  | X | Optional | 40 | 50
| 16 | EIA Input Questionnaire Answers | List |  |  | X | Optional | 40 | 50
| 17 | Technical Note - EIA Design Envelope Assumptions | Report |  |  | X | Mandatory | 40 | 50
| 18 | Foundation Stability Report | Report |  |  | X | Mandatory | 80 | 50
| 19 | Scour Protection Report | Report |  |  | X | Mandatory | 80 | 50
4 |  | Budget estimation of OSS Costs (Electrical and civil structural)
| 1 | Project CAPEX cost estimating | Report | X | X |  | Optional | 80 | 50
| 2 | Project OPEX Cost Estimating | Report | X | X |  | Optional | 80 | 50
| 3 | Project Implementation Plan | Report | X | X |  | Optional | 80 | 50
| 4 | Project Financing Schedule | Report | X | X |  | Optional | 80 | 50
| 5 | Early HV equipment RFI development and assessment of responses | Report | X | X |  | Optional | 80 | 50
5 |  | Prequalification of OEMs, FEED Consultants and EPC(I) contractors & Tender support (Electrical and civil structural)
| 1 | Preparation of FEED MDR | List | X | X | X | Optional | 100 | 55
| 2 | Preparation of FEED high level contract terms | Report | X | X | X | Optional | 100 | 55
| 3 | Adminstration of FEED tendering | Report | X | X | X | Optional | 100 | 70
| 4 | Preparation of FEED evaluation Tender Report | Report | X | X | X | Optional | 80 | 80
| 5 | Preparation of EPC(i) ITT including detailed delivery schedule | Report | X | X | X | Optional | 200 | 60
| 6 | Preparation of EPC(i) high level contract terms | Report | X | X | X | Optional | 100 | 60
| 7 | Preparation of EPC(I) testing and transport requirements | Report | X | X | X | Optional | 200 | 65
| 8 | Development of Pre-Qualification Requirements for EPC(i) contractors | Report | X | X | X | Optional | 100 | 60
| 9 | Administration of EPC(I) Prequalification | Report | X | X | X | Optional | 150 | 100
| 10 | Preparation of EPC(i) Prequalification Report | Report | X | X | X | Optional | 80 | 120
| 11 | Adminstration of EPC(I) tendering | Report | X | X | X | Optional | 200 | 140
| 12 | Preparation of EPC(i) evaluation Tender Report | Report | X | X | X | Optional | 80 | 160
5

## Overall
Task No. | Artefact | Format | PM | Electrical Team | Civl Structural Team | Classification | Est Labour Hours | Timeline | Notes
| Project Management | [6 empty] | Start date plus x days
1 | Project Management Plan (PMP) | Report | X |  |  | Mandatory | 10 | 5
2 | Project Organisation Chart | Chart | X |  |  | Optional | 5 | 5
3 | Project Communication and Interface Matrix | Excel File | X |  |  | Mandatory | 5 | 5
4 | Project Programme (Microsoft Project) | MS Project file | X |  |  | Mandatory | 5 | 5
5 | Quality Management Plan | Report | X |  |  | Mandatory | 10 | 5
6 | Project Master Document Register | Excel File | X |  |  | Mandatory | 5 | 5
7 | Project Risk Register | Excel File | X |  |  | Mandatory | 10 | 15
8 | HSE Register | Excel File | X |  |  | Mandatory | 10 | 15
9 | Monthly Progress Report | Report | X |  |  | Mandatory | 15 | N/A
10 | Weekly Action Tracker | Excel File | X |  |  | Mandatory | 12 | N/A
11 | Final Report / Close out Report (after each Stage) | Report | X |  |  | Mandatory | 20 | 60
Electrical
1 | Electrical Design Basis Statement | Report |  | X |  | Mandatory | 80 | 20
2 | Grid Code Requirement Statement | Report |  | X |  | Mandatory | 20 | 20
3 | Basis HV Topology Report | Report |  | X |  | Mandatory | 60 | 20
4 | Power System Analysis Report | Report |  | X |  | Mandatory | 80 | 65
5 | Power System Model - Digsilent (Steady State) | Model |  | X |  | Mandatory | 80 | 60
6 | Power System Model - PSCAD (Switching) | Model |  | X |  | Mandatory | 80 | 60
7 | OVERALL NETWORK SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 20 | 20
8 | SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 20 | 20
9 | PROTECTION SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
10 | SCADA & CONTROL BLOCK DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
11 | COMMUNICATION BLOCK DIAGRAM | Drawing |  | X |  | Mandatory | 25 | 30
12 | LVAC & LVDC SINGLE LINE DIAGRAM | Drawing |  | X |  | Mandatory | 30 | 30
13 | CELLAR DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
14 | CABLE DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
15 | MAIN DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
16 | COOLER DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
17 | UTILITY DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
18 | MAIN DECK CABLE LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
19 | ROOF DECK LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
20 | ELEVATION LOOKING NORTH LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
21 | ELEVATION LOOKING EAST LAYOUT ARRANGEMENT | Drawing |  | X |  | Mandatory | 40 | 35
22 | Technical requriement specification for main components - EHV GIS | Specification |  | X |  | Mandatory | 20 | 35
23 | Technical requriement specification for main components - MV GIS | Specification |  | X |  | Mandatory | 20 | 35
24 | Technical requriement specification for main components - Power Transformers | Specification |  | X |  | Mandatory | 20 | 35
25 | Technical requriement specification for main components - Shunt Reactors | Specification |  | X |  | Mandatory | 20 | 35
26 | Technical requriement specification for main components - EHV/MV Cables (connections to TF and GIS) | Specification |  | X |  | Mandatory | 20 | 35
27 | Technical requriement specificaiton of earthing, lightning systems | Specification |  | X |  | Mandatory | 25 | 35
28 | Technical requriement specification of Protection, SCADA, Communication systems, Access Control Monitoring, etc. | Specification |  | X |  | Mandatory | 30 | 35
29 | HAZID Workshop (Overall OSS) | Report |  | X |  | Optional | 40 | 35
Civil and Structural
1 | Comparison Studies and assessments - Comparison of anodes and ICCP | Report |  |  | X | Mandatory | 40 | 20
2 | Comparison Studies and assessments - Installation comparison | Report |  |  | X | Mandatory | 40 | 20
3 | Comparison Studies and assessments - High level comparison of topside braced design and stress skin design | Report |  |  | X | Mandatory | 40 | 20
4 | OSS Design Basis - Topside / Jacket | Report |  |  | X | Mandatory | 60 | 30
5 | OSS General Arrangement - Jacket | Report |  |  | X | Mandatory | 60 | 30
6 | OSS J-tube Appurtenance Arrangement | Drawing |  |  | X | Mandatory | 40 | 35
7 | OSS Topside 3-D Model | Model |  |  | X | Mandatory | 150 | 40
8 | OSS Substructure 3-D Model | Model |  |  | X | Mandatory | 150 | 40
9 | OSS Weight Report - Topside/Jacket | Report |  |  | X | Mandatory | 40 | 40
10 | Material Take-off (MTO) - Jacket (Primary steels focused) | List |  |  | X | Mandatory | 40 | 45
11 | Material Take-off (MTO) - Topside (Primary steels focused) | List |  |  | X | Mandatory | 40 | 45
12 | Design Report - Structural designs, Loadout and T&I concept - Jacket | Report |  |  | X | Mandatory | 60 | 45
13 | Design Report - Structural designs, Load out and T&I concept - Topside | Report |  |  | X | Mandatory | 60 | 45
14 | Cost Estimation Report - Topside / Substructure / T&I / Commissioning | Report |  |  | X | Optional | 40 | 50
15 | Preliminary EPCI Project Execution Plan | Report |  |  | X | Optional | 40 | 50
16 | EIA Input Questionnaire Answers | List |  |  | X | Optional | 40 | 50
17 | Technical Note - EIA Design Envelope Assumptions | Report |  |  | X | Mandatory | 40 | 50
18 | Foundation Stability Report | Report |  |  | X | Mandatory | 80 | 50
19 | Scour Protection Report | Report |  |  | X | Mandatory | 80 | 50
Budget estimation of OSS Costs (Electrical and civil structural)
1 | Project CAPEX cost estimating | Report | X | X |  | Optional | 80 | 50
2 | Project OPEX Cost Estimating | Report | X | X |  | Optional | 80 | 50
3 | Project Implementation Plan | Report | X | X |  | Optional | 80 | 50
4 | Project Financing Schedule | Report | X | X |  | Optional | 80 | 50
5 | Early HV equipment RFI development and assessment of responses | Report | X | X |  | Optional | 80 | 50
Prequalification of OEMs, FEED Consultants and EPC(I) contractors & Tender support (Electrical and civil structural)
1 | Preparation of FEED MDR | List | X | X | X | Optional | 100 | 55
2 | Preparation of FEED high level contract terms | Report | X | X | X | Optional | 100 | 55
3 | Adminstration of FEED tendering | Report | X | X | X | Optional | 100 | 70
4 | Preparation of FEED evaluation Tender Report | Report | X | X | X | Optional | 80 | 80
5 | Preparation of EPC(i) ITT including detailed delivery schedule | Report | X | X | X | Optional | 200 | 60
6 | Preparation of EPC(i) high level contract terms | Report | X | X | X | Optional | 100 | 60
7 | Preparation of EPC(I) testing and transport requirements | Report | X | X | X | Optional | 200 | 65
8 | Development of Pre-Qualification Requirements for EPC(i) contractors | Report | X | X | X | Optional | 100 | 60
9 | Administration of EPC(I) Prequalification | Report | X | X | X | Optional | 150 | 100
10 | Preparation of EPC(i) Prequalification Report | Report | X | X | X | Optional | 80 | 120
11 | Adminstration of EPC(I) tendering | Report | X | X | X | Optional | 200 | 140
12 | Preparation of EPC(i) evaluation Tender Report | Report | X | X | X | Optional | 80 | 160